## Slide 1
Summary of Lessons from Previous PI-Led Missions:
Studies and Assessments
Presentation to the 2019 Astrophysics Explorers
Phase A Kickoff
April 23, 2020
Science Office for Mission Assessments (SOMA)
Notes: This set of slides is based on 02/12/2020 PIF-8 presentation slides and the Discovery 2019 Phase A kickoff slides with Step 1 data removed.

## Slide 2
There are four lessons learned studies on the evaluation of Step 1 proposals and Step 2 CSRs that are available on the SOMA homepage. They are:
Common Management Major Weaknesses in Step 1 Proposals
Summary of Lessons from Previous PI-Led Missions March 25, 2020
Instrument Considerations for Step 1 and Step 2 Proposals
Instrument Considerations for Pre-Phase A Proposals
This presentation is an update to #2 without the Step 1 analysis and some edits to the final charts.
SOMA homepage - http://soma.larc.nasa.gov/
TMC Studies and Assessments

## Slide 3
Step 2 Lessons Learned Study Update
Study Questions
What is the history of TMC Risk Ratings?
Are there common causes of major weaknesses?
Study Update
This update adds five new step 2 evaluations that were completed between 2017 and 2019:
Astrophysics MIDEX 2016, Astrophysics MO 2016, Heliophysics MO 2016, Heliophysics SMEX 2016, New Frontiers 4
Step 2 Lessons Learned Study
Results
Conduct a review of formal records of more than 1200 proposals and concept study reports retained by SOMA in the on-site archive library.
  Step 2 Major Weakness Trends and Common Causes (Step 1 results will not be presented today)

## Slide 4
The common causes of Major Weaknesses from 147 CSRs are summarized.
Step 2 Technical Major Weaknesses
Issues with requirements definition and flow down, overstated heritage, and inadequate plans for verification dominate the technical category.
Requirements – These major weaknesses are due to problems with requirements definition, traceability and flow down.
Verification – These weaknesses are due to issues with inadequate plans for verification.
  CSRs with this weakness also often had a major weakness related to requirements, system complexity, or design maturity.
Heritage – These weaknesses are due to issues with the implementation of heritage elements or the support of heritage claims.
  Overstatement of the benefits of the heritage
  Modifications of the heritage element is required but not adequately accounted for in the proposal.
•
Step 2 Common Causes of Major Weaknesses (1 of 4)
Step 2 Lessons Learned Study
Notes: Latest dataset
requirements
verification
mass (twice)
Thermal (twice)
ACS
Image quality
power (twice)
downlink
rideshare plans

## Slide 5
Step 2 Technical Major Weaknesses (continued)
TRLs – These weaknesses are related to overstated TRLs or inadequate technology development plans.
  These findings are primarily instrument related.
Mass Margin – These weaknesses are issues with mass margin or contingency.
  Mass margin major weaknesses still occur but less frequently than in Step 1.
Thermal – These weaknesses are due to inadequate thermal design or performance claims that are not supported.
  These findings are primarily instrument related.
ACS – These weaknesses are issues with attitude determination and control.
  Inadequate description of the pointing budget
  Mismatch between hardware capability and required performance
Optics or Focal Plane – These findings are related to the design and development of the instrument optics and focal plane.
  Overstatement of performance is often cited.
•
Step 2 Common Causes of Major Weaknesses (2 of 4)
Step 2 Lessons Learned Study

## Slide 6
Step 2 Management Major Weaknesses
• 28% are issues associated with key individuals
– Lack of relevant experience among core team
    – Some PM candidates proposed had good management
credentials, but limited or no history of flight project accountability
  – Low time commitments for key members of the core team: Project Manager, Systems Engineer, Flight System Manager, Key Instrument Engineer, etc.
• 28% relate to systems engineering (SE)
  – Often reflects lack of consistency among project elements
  – Most management weaknesses since 2009 are in systems engineering
• 26% are schedule related major weaknesses
  – Inadequate or inappropriately placed schedule reserve
  – Missing key elements
  – Inadequate definition or missing critical path
• 16% are related to management plans
  – Key elements such as risk management are inadequate
Step 2 Common Causes of Major Weaknesses (3 of 4)
Step 2 Lessons Learned Study
Notes: Dragonfly added three additional SE findings
CAESAR added one schedule finding.

## Slide 7
Step 2 Cost Major Weaknesses
• 41% are related to significant and unreconciled differences between the proposed cost and the independent cost estimate
– This finding is often associated with a dispute in the proposer’s underlying assumptions in areas such as technical performance, TRLs, heritage, etc.
• 23% are due to an inadequate basis of estimate
• 21% are due to inadequate cost reserve
– No cost reserve Step 2 major weaknesses since 2009
– Cost reserve was often an issue in proposals with low maturity or overstated heritage
• 15% are related to the credibility or relevance of the supporting cost data
Step 2 Common Causes of Major Weaknesses (4 of 4)
Step 2 Lessons Learned Study

## Slide 8
*Includes only the most common major weaknesses
Sources of Step 2 Systems Engineering
MWs in New Data
Step 2 Lessons Learned Study
The flowdown, traceability, completeness, consistency or stability of the top level mission or flight hardware requirements is flawed
The SE plans or approach, including clearly identifying the roles and responsibilities of the PSE are flawed
Step 2 Systems Engineering Major Weaknesses

## Slide 9
Distribution by Number
TMC Step 2 Risk Distribution Comparison
Distribution by Percentage
Approximately half of all pre-2017 Step 2 CSRs are rated Low risk, with 37% Medium risk and 12% High risk.
Two additional risk ratings (Low-Medium, and Medium-High) were added for the 2017-2019 evaluations. Insufficient data is available to draw conclusions from these data, but the apparent result is the percentage of CSRs rated Low risk has significantly decreased. The small data set shows almost half of the CSRs rated as either Low or Low-Medium risk.
Step 2 Lessons Learned Study
Notes: Updated with NF-4 Data. 1 additional Medium and 1 additional Medium-High.
Added the word almost to the final sentence.

## Slide 10
Step 2 Major Strengths
Step 2 Lessons Learned Study
Notes: Updated to Include NF-4

## Slide 11: Step 2 Risk Ratings of Selected Step 1 Proposals
The risk rating for most of this small set of missions selected for step 2 either remained the same (21/47) or got worse (22/47). This result may be explained, in part, by more detailed reviews and less “benefit of the doubt” given in Step 2. Between 2017 and 2019 (highlighted in yellow), six Low, seven Medium, and one High Risk proposal were selected. Of these selected proposals, one Medium-High, one Medium Risk, two Low-Medium Risk and two Low Risk CSRs were down-selected for implementation.
28 (6)
Step 1 Low Risk
18 (7)
Step 1 Medium Risk
16 Step 2 Low Risk
18 Step 2 Medium Risk
6 Step 2 High Risk
14
11
7
6
47 Step 1 Proposals Selected
47 Rated CSRs
14 (2)
Implementation
3 Step 2 Medium-High Risk
4 Step 2 Low-Medium Risk
3
2 (2)
2
1
1 (1)
2
18 Missions
Implemented
Step 2 Lessons Learned Study
1 (1)
1 (1)
Step 1 High Risk
1

## Slide 12
Step 2 Summary
SOMA has directed the evaluation of 147 Step 2 CSRs submitted by PI-led teams since the office was formed.
Are there common causes of major weaknesses in Step 2 TMC reviews? Yes! Certain types of weaknesses persist, specifically:
Proposed costs with their supporting BOEs could not be validated using independent cost models.
The flowdown, traceability, completeness, consistency or stability of the top level mission or flight hardware requirements is flawed.
Development schedules that lack sufficient detail to verify their feasibility, have missing elements, allocate too little time for typical activities without sufficient rationale (e.g., AI&T), or have too little funded schedule reserve for the identified development risks.
Inadequate verification plans.
Overstated instrument or Flight System TRLs (usually based on overstated heritage) or inadequate plans to demonstrate existing component technologies in newly integrated systems or operating in new environments.
Inadequate margins for technical resources. Mass is the most common issue.
Thermal design is not demonstrated to be viable.
ACS performance claims are not supported.
Lack of time commitment from key management team
Step 2 Lessons Learned Study
Notes: Updated the number of CSRs to 147 from 145 in the first line.